## Risk_Register
AG3 Risk Register
ID | Risk event | Threat source | Threat event and vulnerability | Inherent likelihood | Inherent impact | Inherent score | Inherent rating | Current controls | Residual likelihood | Residual impact | Residual score | Residual rating | Control gap | Response | Required treatment and acceptance evidence | Owner | Priority
R01 | Credential disclosure and privileged-account compromise | Adversarial | Live-looking credentials were found, which could be reused in a repository or privileged secret by an attacker. | 5 | 5 | 25 | Critical | Encryption of protected files and backup identity and scope; repository encryption. | 4 | 5 | 20 | Critical | 5 | Mitigate / avoid | Check if any values were true. If so, rotate them, remove them from documents and repository history, invalidate sessions and show the restricted identity does work without root credentials. | Faysal / Sourabh | Immediate
R02 | Intercept and/or modify traffic in case of a failure | Adversarial | APP01 is accessible to MinIO via its transport metadata and credentials through HTTP over TCP 9000 and is susceptible to network interception. | 4 | 4 | 16 | High | Segmented VLANs; Restic repository encryption. | 3 | 4 | 12 | High | 4 | Mitigate | Update Restic endpoint; retest backup and restore with pfSense; enable MinIO TLS with trusted certificates. | Faysal / Akib | Immediate
R03 | Backup deletion or ransomware impact | Adversarial | Snapshots were not proven to be immutable; they may be deleted by privileged use of MinIO or credentials held by APP01. | 4 | 5 | 20 | Critical | Separate Backup VLAN; scoped service identity; repository integrity checks. | 3 | 5 | 15 | High | 5 | Mitigate | Use Object Lock/versioning or immutable copy; prohibit delete for normal identity; maintain a second copy in an alternate location or recovery copy offline. | Faysal | High
R04 | Unproven full disaster recovery | Structural | Demonstration files and the SQL artefact was restored, but the whole Nextcloud service was not rebuilt and tested on a clean server. | 4 | 5 | 20 | Critical | Restic snapshots; documented restore concept; integrity check passed. | 4 | 4 | 16 | High | 4 | Mitigate | Timed restore of data, application and database to clean servers; verify user logon and access to files; document actual RTO and RPO. | Sourabh / Faysal | Immediate
R05 | Single-disk backup failure | Structural | BKP01 has one disk and no RAID, replication or second independent copy. | 3 | 5 | 15 | High | MinIO service restart; free-capacity check; repository integrity check. | 3 | 4 | 12 | High | 3 | Mitigate / transfer | Add redundant storage, independent copy; monitor SMART, capacity and MinIO health; document replacement procedure. | Faysal | High
R06 | Backups that aren't done or that have not been taken recently. | Structural | Most recent automation can fail if no routing is available; most recent automated snapshot might not be current. | 4 | 4 | 16 | High | Four-hour schedule; success/failure log; Wazuh custom alerts on APP01. | 3 | 4 | 12 | High | 4 | Mitigate | Alert on explicit failure and missing expected success; set a response SLA; validate the timer post network change; trend the age of backup independent of cumulative number of events. | Sourabh / Tanvi | Immediate
R07 | Excessive capacity and capacity starving | Accidental | Only dry-run retention was tested; old snapshots might end up being accumulated or old recovery points deleted manually. | 3 | 4 | 12 | High | Proposed keep-last/keep-daily policy; current capacity visible. | 3 | 3 | 9 | Moderate | 3 | Mitigate | Endorse retention policies, automate forget/prune, logging; test on non-production set; alert for capacity levels. | Faysal / Sourabh | High
R08 | Network segmentation bypass or drift | Accidental | Production VLAN membership is not enforced on unmanaged switch; there may be a drift in configuration and thus production VLANs may be exposed. | 4 | 4 | 16 | High | pfSense VLANs; default-deny policy; 15/15 executed firewall tests. | 3 | 4 | 12 | High | 4 | Mitigate | Managed VLAN switch, export pfSense configuration, schedule review of rules and repeat positive/negative acceptance tests. | Akib | High
R09 | After the monitoring path is set to obsolete, all the isolation is weakened. | Accidental | Previous rules were made for BKP01 to MON01 on 1514/1515, as it was the last isolation no-agent design. | 3 | 4 | 12 | High | Final architecture intentionally monitors backups through APP01 only. | 3 | 3 | 9 | Moderate | 3 | Avoid | Remove BKP01 to MON01 (Allow Only); Retain only required APP01 to BKP01 (Allow Only); Retest and capture firewall deny evidence. | Akib / Tanvi | Immediate
R10 | Monitoring outage or blind spot | Structural | MON01 sleep, agent failure or rule changes can prevent alerts; no direct telemetry of host MON01. | 4 | 4 | 16 | High | APP01 agent; Wazuh dashboard; custom rules; agent health visible. | 3 | 4 | 12 | High | 4 | Mitigate | Always keep MON01 on, add heartbeat/missing-event alert, backup Wazuh config and monitor MinIO indirectly using health/jobs checks. | Tanvi | High
R11 | Unauthorised access and credential attacks | Adversarial | Business Information or Administration may be compromised due to password guessing or compromised accounts. | 4 | 5 | 20 | Critical | Failed-login detection; Nextcloud groups; administrator TOTP; segmented management. | 3 | 4 | 12 | High | 8 | Mitigate / deter | Implement MFA for all privileged accounts; establish password/lockout policies, review accounts every 3 months, save and review alerts. | Sourabh / Tanvi | High
R12 | Modification of file or configuration files without proper permission. | Adversarial | Nextcloud, script or system files might be deleted, added or changed due to malware, ransomware or due to errors. | 4 | 4 | 16 | High | Wazuh FIM; separated backup repository; Nextcloud access controls. | 2 | 4 | 8 | Moderate | 8 | Mitigate | Focus FIM to critical paths; alert on changes to backupscripts, changes to configuration; keep ruleID's and timestamp; only add automatic containment after safe testing. | Tanvi / Sourabh | Medium
R13 | Unpatched software or insecure configuration | Accidental | Known vulnerabilities or weak settings may allow compromise. | 4 | 4 | 16 | High | Vulnerability detection; APP01 patch verification; CIS hardening improved score from 45% to 49%. | 3 | 4 | 12 | High | 4 | Mitigate | Formal monthly patch cycle; Prioritize the exposed CVEs; Rollback testing of remediation for CIS failures; Rescan and evidence closure. | Sourabh / Tanvi | High
R14 | Single point of failure for firewall and/or monitoring | Structural | A single pfSense instance (or MON01) can cause interruption of routing, policy or security visibility. | 3 | 5 | 15 | High | Saved configuration; service restart; segmented design. | 3 | 4 | 12 | High | 3 | Mitigate / transfer | Back up configuration; document rebuild, test restore; consider up's and redundant production components. | Akib / Tanvi | Medium
R15 | Weak governance of evidence and leakage of data sensitive | Accidental | Screenshots and reports may expose passwords, tokens, addresses or personal data. | 4 | 4 | 16 | High | Some files use placeholders and restricted permissions. | 4 | 4 | 16 | High | 0 | Avoid / mitigate | Redact evidence; rotate disclosed values; prohibit secrets in Git/assessment files; use secret scanning and controlled evidence access. | Team | Immediate

## Risk_Matrix
Risk Matrix
Impact
Likelihood |  | Insignificant (1) | Minor (2) | Moderate (3) | Major (4) | Severe (5) | Score | Rating | Score | Likelihood | Interpretation | Score | Impact | Interpretation
| Almost Certain (5) | 5 | 10 | 15 | 20 | 25 | 20–25 | Critical | 1 | Rare | Unlikely in the prototype life, strong prerequisites or controls. | 1 | Insignificant | Minor inconvenience: No material data/service effect.
| Likely (4) | 4 | 8 | 12 | 16 | 20 | 12–19 | High | 2 | Unlikely | Can happen, but unlikely to do so unless there are unusual circumstances. | 2 | Minor | There is some rework or minimal disruption, and it is easy to recover.
| Possible (3) | 3 | 6 | 9 | 12 | 15 | 6–11 | Moderate | 3 | Possible | Realistic opportunity or warning signs of credible event. | 3 | Moderate | Some parts of the material are unavailable for operation, some data are not exposed or cannot be recovered.
| Unlikely (2) | 2 | 4 | 6 | 8 | 10 | 1–5 | Low | 4 | Likely | Predicted to happen or has happened in test. | 4 | Major | Prolongs outage, substantial data loss/exposure or recovery goal failure.
| Rare (1) | 1 | 2 | 3 | 4 | 5 |  |  | 5 | Almost certain | Repeated, unmasked or known but not preventable. | 5 | Severe | Continued disruptions to business, significant catastrophic breach or loss of irreplaceable key information.