# 11. Risk identification and mitigation plan

At first, we identified the technical, security, schedule and teamwork risks of our project. We used likelihood and impact values from 1 to 5. Then we multiplied these values to get the risk score (NIST 2024). The register will not be kept as a one-time document. We will review it in every weekly meeting and update the treatment when the project condition changes.

| ID | RISK | L | I | Rating | Treatment | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| R-01 | Ransomware or stolen credentials can delete the online backup. | 4 | 5 | 20 Extreme | Use a separate backup VLAN, service account, retention and optional offsite copy. | Faysal |
| R-02 | The backup job completes but the data cannot be restored. | 4 | 5 | 20 Extreme | Run weekly checks, sample restore and a full timed recovery. | Faysal |
| R-03 | Recovery misses the RTO because too many steps are manual. | 4 | 4 | 16 Extreme | Use scripts, a clean restore target, a priority sequence and rehearsal. | Faysal |
| R-04 | A lost MFA device locks a user out. | 3 | 3 | 9 High | Use recovery codes, a controlled emergency process and written enrolment steps. | Shourab |
| R-05 | Wazuh misses the mass file change or creates too many alerts. | 3 | 4 | 12 High | Tune file paths and thresholds and generate known test events. | Tanvi |
| R-06 | The lab computer does not have enough RAM, CPU or storage. | 4 | 3 | 12 High | Reduce VM size, start systems in stages, monitor storage and split hosting if needed. | Akib |
| R-07 | The safe simulation changes a file outside the test folder. | 2 | 5 | 10 High | Use an exact allowed path, dry-run mode, synthetic data, snapshot and mentor approval. | Tanvi |
| R-08 | Passwords, keys or real data are uploaded to GitHub. | 3 | 5 | 15 High | Use synthetic data, .gitignore, secret checks and peer review before pushing. | All |
| R-09 | The work is not divided equally or a milestone is missed. | 3 | 4 | 12 High | One owner for every card, weekly evidence and early task redistribution. | Rotating leader |
| R-10 | The cloud cost becomes higher than the approved budget. | 3 | 3 | 9 High | Use a budget cap, alerts and delete unused storage after testing. | Cloud owner |
| R-11 | An internet outage affects the cloud copy or final demo. | 3 | 3 | 9 High | Keep the local MVP independent and prepare a recorded fallback. | Demo lead |
| R-12 | Extra features stop the team from finishing the MVP. | 4 | 4 | 16 Extreme | Freeze the MVP and move new ideas to stretch goals after Week 9. | All |

From the above table we can see that backup deletion, failed restoration, manual recovery and scope growth have the highest initial scores. So these risks will be checked early instead of waiting for final testing.

# 12. Quality management plan (Kerzner 2017)

Our quality approach is based on checking every important output. We will not mark a task as complete only because the document or configuration is created. At first, another member will review it. Then we will connect it with a requirement and test it. Finally, the result and evidence will be stored in the repository.

| Quality area | What we will do | Evidence |
| --- | --- | --- |
| Requirements | Give every Must requirement an ID and connect it to design, implementation and testing. | A reviewed traceability matrix with no missing Must requirement. |
| Technical correctness | Peer review the firewall, scripts, hardening and recovery commands before integration. | A pull request or review record and corrected configuration. |
| Security and privacy | Use synthetic data, remove secrets, apply least privilege and keep the repository private. | Secret scan, repository review and access-test result. |
| Reproducibility | Store configurations, scripts, example environment files and rebuild steps. | A second member can follow the runbook successfully. |
| Testing | Record version, operator, time, expected result, actual result and evidence for each test. | Completed acceptance-test register with Pass or Fail result. |
| Recovery | Measure RPO and RTO and compare file count, hashes and application access. | Timed logs, manifest comparison and user-access check. |
| Documentation | Use the same terms, captions, Harvard references and final proofreading. | A final checklist reviewed by a member other than the writer. |
| Demonstration | Practice the complete scenario and keep a recorded backup. | Demo checklist and fallback recording. |

From the above quality plan, we can see that evidence is required for all main work. This method will reduce the chance of accepting a configuration that looks correct but does not work.

# 13. Tools, technologies and resources

We compared the tools based on cost, available documentation, technical function and suitability for a student lab. Our aim was to select tools that can build a real system without a high license cost.

| Resource | How we use it | Why we selected it |
| --- | --- | --- |
| GitHub private repository | Store configurations, scripts, diagrams, documents, tests and AI-log.md. | It gives time-stamped evidence and supports review. Secrets must not be uploaded. |
| GitHub Projects | Use a Kanban flow from Backlog to Done. | It shows the owner and progress of each task. |
| Microsoft Teams | Keep meetings, decisions, troubleshooting and mentor discussion. | It keeps a searchable record of why a decision was made. |
| VirtualBox, VMware, Proxmox or GNS3 | Run the firewall, servers and client in a virtual environment. | It meets the real-build requirement. The final platform depends on team hardware. |
| pfSense | Create VLAN routing, firewall rules and syslog. | It is widely documented and suitable for a small network lab. |
| Ubuntu LTS and Nextcloud | Run the business record portal and database. | It supports accounts, groups, files, MFA and logs. |
| Wazuh | Collect login, file integrity, firewall and vulnerability events. | It is an open-source monitoring platform suitable for the security part. |
| Restic and MinIO | Create encrypted backups and store them in an isolated S3-compatible repository. | They support scripting, snapshots, checking and recovery testing. |
| Python, Bash and PowerShell | Automate backup, test data, verification and network tests. | Automation makes the work repeatable and meets the capstone requirement. |
| Optional cloud storage | Keep a second encrypted backup outside the local lab. | This is a stretch goal and the cost must be approved first. |

From the above tools we found that the main MVP can be completed using open-source or community software. The team only needs to choose one virtualization platform. Using many platforms together can make the project difficult to rebuild.

## 13.1 Indicative resource and budget plan

| Item | Quantity / allowance | Estimated cost | Control |
| --- | --- | --- | --- |
| Existing student computers or shared virtual host | Team provided | AU$0 direct purchase | Check capacity in Week 2 and start VMs in stages if required. |
| Community and open-source software | All main MVP tools | AU$0 license cost | Check license conditions and edition limits. |
| Optional cloud object storage | Small test allocation | Maximum AU$50 for the team | Use budget alerts and delete the storage after the project. |
| External drive or extra storage | Only when required | [Need an approved amount] | Get approval first and store synthetic data only. |
| Contingency | 10% of the approved cash budget | [Amount will be provided later] | Use only after team agreement. |

# 14. Feasibility analysis

A technical feasibility analysis is carefully carried out in order to determine a professional investment strategy (Gürtürk, Erdem & Uçar 2024). After selecting the tools and project scope, we analyzed whether the project can be completed in this term. We checked the technical, schedule, operational, economic, safety and teamwork feasibility.

| Feasibility area | Assessment |
| --- | --- |
| Technical feasibility | The tools can run on student virtualization hardware and have clear setup documents. We will test resource use and integration early. |
| Schedule feasibility | The roadmap builds a network skeleton and one thin working process by the middle of the term. Stretch goals will wait until the MVP is stable. |
| Operational feasibility | The user will use a web portal, TOTP and short runbooks. This is suitable for a small office without dedicated IT staff. |
| Economic feasibility | The MVP mainly uses existing hardware and free or community software. Cloud use is optional and capped. |
| Safety and ethical feasibility | Only synthetic data and a limited test directory will be used. Real ransomware and uncontrolled destructive testing are excluded. |
| Team feasibility | Every member has one technical workstream. Weekly commits, Kanban updates and mentor demonstrations will show problems early. |

From the above analysis we can see that the project is feasible if the team completes the main build early and controls the scope. The biggest limitation is hardware capacity and integration time, so these will be tested before the final weeks.

# 15. Professional, ethical and security considerations

The team must work responsibly and safely because this project involves security and data recovery. We will use the following rules during the project (NIST 2018):

Use synthetic data only and do not collect unnecessary personal or business information.

Keep the repository private and remove passwords, tokens, public IP addresses and identifying screenshots before submission.

Do not run real ransomware or test a system without clear ownership and permission.

Use dry-run mode by default and restrict the simulation to the approved test folder.

Tell users what monitoring is used and collect only the events needed for security and recovery.

Check software licenses and give credit for third-party code, documents and diagrams.

Record important AI use in AI-log.md, check the output and understand every submitted artefact.

Refer legal, privacy, insurance and notification questions to qualified advisers instead of giving legal advice.

So, from these considerations we decided that safety and privacy will be included in the technical design, not only written at the end. The simulation, screenshots and repository will be checked before they are shared.

# References

Gürtürk, M, Erdem, M & Uçar, F 2024, ‘Solar energy technical feasibility comparison: an alternative proposal for the industry’, Energy Efficiency, vol. 17, article 41. DOI: 10.1007/s12053-024-10226-9

Kerzner, H 2017, Project management: a systems approach to planning, scheduling, and controlling, 12th edn, E-book, John Wiley & Sons, Hoboken, New Jersey.

NIST 2024, Cybersecurity Framework (CSF) 2.0, National Institute of Standards and Technology, viewed 25 July 2026, https://doi.org/10.6028/NIST.CSWP.29

NIST 2018, Risk Management Framework for Information Systems and Organizations: A System Life Cycle Approach for Security and Privacy (SP 800-37 Rev. 2), National Institute of Standards and Technology, viewed 25 July 2026, https://doi.org/10.6028/NIST.SP.800-37r2