COIT20265
NETWORKS AND INFORMATION SECURITY PROJECT

Project Proposal

AG-3: Cyber Resilience for an Agribusiness Back Office

Group PG5

Group members:

Ashraful Abedin Shourab (12298592)

Akib Hossain (12304711)

Sheikh Tanvi Mahmud (12297656)

Md Mahafuz Faysal (12281612)

Project mentor: Dr. Fariza Sabrina
Date: 3/08/2026

Table of Contents

Executive summary	3

1 Project background and justification	3

1.1 Organisational context	3

1.2 Business justification	4

1.3 Alignment with the AG-3 scenario and capstone expectations	4

2 Problem statement and project objectives	4

2.1 Problem statement	4

2.2 Project aim	4

2.3 SMART objectives	4

3 Innovative aspects and proposed value	5

4 Project scope, assumptions and constraints	6

4.1 In scope	6

4.2 Out of scope	6

4.3 Assumptions	6

4.4 Constraints	6

5 Stakeholder analysis	6

6 High-level requirements and success criteria	8

6.1 Functional requirements	8

6.2 Non-functional requirements	8

6.3 Definition of MVP (Minimum Viable Product) and stretch goals	9

7 Proposed solution and technical architecture	9

7.1 Selected solution	9

7.2 Logical architecture	10

7.3 Proposed components	11

7.4 Proposed firewall policy	11

7.5 Delivery and evaluation method	12

8 Work decomposition and deliverables	12

9 Delivery roadmap	13

10 Team structure, roles and responsibilities	14

10.1 Proposed team roles	14

10.2 RACI matrix	14

10.3 Task leads for major deliverables	14

11. Risk identification and mitigation plan	15

12. Quality management plan	16

13. Tools, technologies and resources	17

13.1 Indicative resource and budget plan	17

14. Feasibility analysis	18

15. Professional, ethical and security considerations	18

16. Communication, Governance and Progress Evidence	19

16.1 GitHub Repository Structure and Commit Discipline	19

16.2 Kanban Card-Naming Rules	20

16.3 Microsoft Teams Channel Structure and Meeting Cadence	20

16.4 AI Transparency and the AI-log	21

16.5 Weekly Proof Checklist	21

17. Group Contribution Declaration	21

18. Conclusion	22

References	23

Appendix C — Final Integration Checklist	24

# Executive summary

Plains Pastoral Co. is a small family owned agricultural business and it is highly depends on digital systems for its daily work. The company use accounting records, livestock and crop information, supplier portal and online sales data. But there is no dedicated IT staff and the security is very limited. So if a ransomware attack happen at harvest time then the normal business can stop and important data can be lost.

For this reason we are proposing a practical cyber resilience system. The system will not only try to prevent an attack, it will also detect the problem and recover the business data. We will build a virtual office environment with pfSense firewall, Nextcloud business portal, Wazuh monitoring, Restic backup and MinIO isolated storage. The users will use password with TOTP multi factor authentication and they will only get access according to their role.

The main outcome of this project is to prove that the backup really works. We will make a safe ransomware-loss simulation by using synthetic files only. Then we will detect the file changes, select a clean backup and restore the priority files and the business portal. The recovery time objective and recovery point objective will be measured so that the result is not only a claim.

The project will follow the capstone requirement of build, test and show the real system. GitHub, GitHub Projects and Microsoft Teams will be used to keep evidence of every member work. So the final project will give Plains Pastoral Co. a simple and affordable method for protection, monitoring, backup and recovery.

# 1 Project background and justification

## 1.1 Organisational context

Plains Pastoral Co. is presented as a digitally dependent small agribusiness. The office keeps financial records, supplier information, livestock records, crops records and online sales information. These data are used for payment, reporting, production planning and customer service. A long outage can create serious problem because the work cannot be completed normally.

The company had no dedicated IT staff. So the security system should not be too complicated or too expensive. It should be easy to operate and there should be a clear recovery procedure. For the university project we will use synthetic data and a virtual environment, so no real customer or company data will be used.

## 1.2 Business justification

The main reason for doing this project is to keep the important business records available after a cyber attack or outage. It is quiet impossible to stop the all cyber attack, so there should be a method in place for detection and recovery. The project will address the following business needs:

Reduce the chance that a stolen password gives direct access to business records.

Limit the spread of an attack by using network separation and least privilege.

Give alerts for failed logins, unusual file changes, firewall blocks and backup failures.

Keep encrypted backup copies away from normal office users and test the restore process.

Give the small business a short and repeatable recovery procedure instead of depending on one person knowledge.

## 1.3 Alignment with the AG-3 scenario and capstone expectations

The AG-3 scenario asks for enforced identity and MFA, system hardening, monitoring, backup and recovery that meet RTO and RPO. It also asks for a live recovery after a simulated ransomware loss. Our proposal directly covers these points.

The project will be a real multi component build in a virtual environment. We will configure the controls, automate the backup, test the network and show one complete workflow. GitHub, GitHub Projects and Microsoft Teams will also show who did the work and when the work was completed.

# 2 Problem statement and project objectives

## 2.1 Problem statement

Problem statement: Plains Pastoral Co. depends on digital records but it does not have dedicated IT staff, strong identity control, central monitoring or a proven recovery process. The company needs an affordable and easy system that can reduce ransomware damage and restore priority work within the agreed RTO and RPO.

## 2.2 Project aim

The aim of this project is to design, build, connect and test a practical cyber resilience environment for a small agribusiness. The system will show protection, detection, containment, backup and recovery by using a safe live demonstration.

## 2.3 SMART objectives

| ID | Objective | How we will prove it |
| --- | --- | --- |
| OBJ-01 | Build a multi component back-office environment by Week 7. | pfSense, APP01, MON01, BKP01 and the client start properly and communicate only through approved network paths. |
| OBJ-02 | Apply identity and least privilege control by Week 8. | All test users use TOTP MFA and an unauthorised user cannot open a restricted folder. |
| OBJ-03 | Complete and record the hardening baseline by Week 8. | Evidence shows patching, SSH restriction, service reduction, TLS and protected administration. |
| OBJ-04 | Centralise the security monitoring by Week 9. | Wazuh receives login, file change, firewall and backup events and shows the test alerts. |
| OBJ-05 | Automate encrypted backup by Week 9. | Restic creates scheduled snapshots in the isolated MinIO storage and records success or failure. |
| OBJ-06 | Complete the tested recovery by Week 11. | Priority files restore within two hours, full portal within four hours and the effective RPO is four hours or less. |
| OBJ-07 | Produce a reproducible and properly evidenced project by Week 13. | The repository contains configuration, scripts, runbooks, tests, traceability and individual contribution evidence. |

# 3 Innovative aspects and proposed value

The innovation is not only one new product. The new value comes from connecting affordable security controls into one recovery centred process. The system will not say the backup is successful until the team can restore the files and check them. This makes the project more useful for a small company.

| Innovative aspect | Practical value |
| --- | --- |
| Recovery as a tested security control | The backup is accepted only after a clean restore, file count check and hash check are completed. |
| Safe ransomware-loss simulation | We will change files only inside a synthetic test folder, so recovery can be tested without using real malware. |
| Isolated backup path | Normal office users will not have network access or backup credentials, so a compromised user has less chance to delete the backup. |
| Monitoring of recovery controls | Backup failure, missing snapshot and integrity result will be monitored with login, firewall and file change events. |
| Small team usability | We will use simple scripts, short runbooks and clear decision steps instead of a very complex enterprise system. |
| Optional offsite resilience | A second encrypted cloud backup can be tested as a stretch goal for complete local site loss. |

# 4 Project scope, assumptions and constraints

## 4.1 In scope

Business impact priorities, stakeholder needs and recovery requirements.

A virtual environment using pfSense, Ubuntu/Nextcloud, Wazuh, MinIO/Restic and one Windows office client.

Separate office, server, security, backup and management networks.

Named users, role based access and TOTP multi factor authentication.

A documented operating system, application and firewall hardening baseline.

Central logging, file integrity monitoring and selected security alerts.

Automated encrypted backup, retention, verification and a tested recovery runbook.

A safe ransomware-loss simulation using synthetic files only.

Acceptance tests, measured RTO/RPO, risk register and quality checks.

GitHub, GitHub Projects, Microsoft Teams and AI-log evidence.

## 4.2 Out of scope

Using or moving real financial, personal or commercially sensitive client data.

Running real ransomware, destructive malware or attacks against another system.

Providing a production 24/7 managed security service.

Building enterprise high availability, multi-site clustering or a full commercial identity platform.

Giving legal, insurance, tax or regulatory advice.

Buying production hardware or entering a long-term cloud contract.

## 4.3 Assumptions

The team will have computers or a shared virtual host with enough RAM and storage.

The mentor will confirm the RTO, RPO and safe test scope before the recovery test.

Synthetic records will represent the priority business files.

Community or evaluation versions of the tools will be enough for the project demonstration.

Every member will do technical build, configuration or testing work and not only documentation.

## 4.4 Constraints

The project has only a 12 to 13 week academic term.

Student computer capacity, internet connection and cloud budget are limited.

The team members have different availability and technical experience.

The recovery demonstration must be safe and cannot use real malware.

The project should be accessible to the team and rebuildable from the repository.

# 5 Stakeholder analysis

Different people need different result from this project. So we identified their main need, their influence and how we will communicate with them.

| Stakeholder | Main need | Influence | How we will engage |
| --- | --- | --- | --- |
| Owner/manager | Business continuity, low cost and confidence in recovery. | High | Confirm priorities, RTO/RPO and show short progress demonstrations. |
| Office staff | Reliable access without a difficult login process. | High | Use easy TOTP enrolment, role based folders and a short guide. |
| Bookkeeper/accountant | Correct and available financial records. | Medium | Classify priority records, use four-hour RPO and validate restored data. |
| Suppliers/customers | Protection and availability of contact and transaction information. | Medium | Use least privilege, encryption and logging. Only synthetic data will be used in the project. |
| Project team | Feasible technical work, learning and fair contribution. | High | Use owned workstreams, GitHub commits, Kanban cards and weekly updates. |
| Project mentor | Safe project, capstone depth and clear evidence. | High | Review risks and scope, attend meetings and see the running system. |
| CQUniversity assessor | Clear marking criteria alignment and professional presentation. | High | Use clear sections, tables, references and contribution declaration. |

# 6 High-level requirements and success criteria

This section explains what the system must do and how we will check it. First, we have listed the functional requirements. These are the actions that the system must perform. Second, we have listed the non-functional requirements. These describe recovery time, security, cost, usability and safety. Finally, each important requirement has a clear acceptance measure so the team can prove the result.

## 6.1 Functional requirements

| ID | Requirement | Priority | Acceptance measure |
| --- | --- | --- | --- |
| FR-01 | Authenticate every named user before they can access the business records. | Must | An unauthenticated request is denied or moved to the login page. |
| FR-02 | Require TOTP (Time-based One-Time Password) and MFA (Multi-Factor Authentication) for normal and administrator accounts (Australian Cyber Security Centre 2024) | Must | Password-only login fails and a valid second factor succeeds. |
| FR-03 | Use roles so each user can access only the folders needed for the job. | Must | A restricted user cannot read an unauthorised folder. |
| FR-04 | Separate the office, server, security, backup and management networks. | Must | Approved traffic works while other inter-VLAN traffic is blocked and logged. |
| FR-05 | Apply and document a hardening baseline. | Must | The required operating system, application and management settings. |
| FR-06 | Collect login, firewall, system and file integrity events in one place. | Must | Wazuh will show the generated events with the correct source and time. |
| FR-07 | Create encrypted application backups at least every twenty-four hours. | Must | The scheduled job creates a new snapshot and records success. |
| FR-08 | Stop normal office users from reaching the backup repository. | Must | Direct network and credential access attempts are denied. |
| FR-09 | Check the backup repository and complete sample restores. | Must | Verification and sample-restore logs show a successful result. |
| FR-10 | Run a safe ransomware-loss simulation using synthetic data. | Stretch | Only the approved test folder changes and a monitoring alert is created. |
| FR-11 | Restore the priority records and portal from a clean snapshot. | Must | The files and application are restored and checked within the recovery targets. |
| FR-12 | Keep an offsite encrypted copy and an automated restore test. | Stretch | A separate copy exists and a scheduled validation report is produced. |

## 6.2 Non-functional requirements

| ID | Quality area | Target |
| --- | --- | --- |
| NFR-01 | Recovery point objective | The maximum loss of priority business data will be twenty-four hours. |
| NFR-02 | Recovery time objective | Priority files will be restored within two hours and the full portal within four hours. |
| NFR-03 | Security | The system will use MFA (Multi-Factor Authentication), least privilege, encryption and isolated backup access. |
| NFR-04 | Usability | A normal user will be able to log in and retrieve a file by following a one-page guide. |
| NFR-05 | Cost | The MVP (Minimum Viable Product) will use free, community or evaluation tools and remain within the approved budget. |
| NFR-06 | Auditability | Security events, backups and recovery actions will contain a time and responsible user. |
| NFR-07 | Reproducibility | A second member will be able to rebuild or recover the system by following the repository instructions. |
| NFR-08 | Safety and privacy | Only synthetic data and a limited simulation folder will be used. |

## 6.3 Definition of MVP (Minimum Viable Product) and stretch goals

The MVP is the minimum complete system that the group must deliver. Stretch goals will begin only after the MVP is stable. This helps us control the scope and finish the most important work first.

| Category | Committed outcome |
| --- | --- |
| MVP (Minimum Viable Product) | A working environment with MFA (Multi-Factor Authentication), role access, hardening, network segmentation, Wazuh monitoring, encrypted isolated backups and a live timed recovery after a safe simulated loss. |
| Stretch 1 | A daily encrypted copy in a separate cloud account with independent credentials and retention. |
| Stretch 2 | Automatic backup checking and restore it to a temporary clean folder with an alert when it fails. |
| Stretch 3 | A short security awareness package and a continuity exercise for non-technical staff. |
| Stretch 4 | Repeatable configuration by using Ansible or another automation method. |

# 7 Proposed solution and technical architecture

## 7.1 Selected solution

We will select a virtual open-source lab with an optional cloud backup copy. First, this option gives enough technical depth because the team must build several connected components. Second, it will keep the direct cost low because most tools are free or community based. Third it allows the team to test the full process safely with synthetic data.

The main systems are pfSense, Nextcloud, Wazuh, Restic and MinIO. Each system has different job, but the final value comes from their integration. The office user will log in with MFA (Multi-Factor Authentication), access the portal through the firewall, create monitored events and rely on an isolated backup for recovery. These controls are consistent with Essential Eight mitigation strategies recommended by Australian cyber security center to reduce the likelihood and impact of cyber incident (Australian Cyber Security Center 2024)

## 7.2 Logical architecture

Figure 1. Proposed AG-3 logical architecture and network segmentation.

The diagram above, shows the logical architecture of our AG-3 cyber resilience system. We divided the network into different VLANs so that each part of the system can work separately and securely. The pfSense firewall is placed in the center of the architecture. It controls all communication between the internet and the internal VLANs. It also decides which device can communicate with another device. (National Institute of Standards and Technology 2009; National Institute of Standards and Technology 2022; Netgate 2026).

The office VLAN 10 contains the Windows 11 client computer. This computer represents the normal office user of Plains Pastoral Co. The user accesses the business-record portal through a web browser. TOTP multi-factor authentication is also used during login. The client connects to the Nextcloud server through HTTPS port 443. This protects communication between the user and the server. (National Institute of Standards and Technology 2020).

The server VLAN 20 contains the Ubuntu application server. Nextcloud and its database are installed on this server. It will stores the synthetic accounting, supplier and agribusiness records used in our project. A Wazuh agent and Restic client are also installed on this server. The Wazuh agent sends security information to the monitoring server, while Restic creates encrypted backups of the business data. (National Institute of Standards and Technology 2022).

The security VLAN 30 contain the Wazuh SIEM server. It receive security events from the application server and other connected systems through port 1514 and 1515. Wazuh monitors login failures, file changes, vulnerabilities and other suspicious activities. This helps us detect a possible attack and understand what happened during the incident. (National Institute of Standards and Technology 2022).

The backup VLAN 40 contain the MinIO backup server. The encrypted backups of restic client is sends to MinIO through S3 port 9000. Normal office users cannot directly access this VLAN. For this reason, ransomware on the office computer should not easily reach or damage the backup files. An optional encrypted offsite copy can also be created to protect the data if the local environment is completely lost. (National Institute of Standards and Technology 2020; National Institute of Standards and Technology 2022).

Finally, management VLAN 99 will be used  for only the administrator workstation and management interfaces. Access to this VLAN is restricted because it contains sensitive administrative services. Overall, this architecture uses segmentation, MFA, monitoring and isolated backup storage. These controls work together to protect the business system and allow us to recover the data after a simulated ransomware incident. (National Institute of Standards and Technology 2020; National Institute of Standards and Technology 2022).

## 7.3 Proposed components

| Component | Purpose | Resources | Main control |
| --- | --- | --- | --- |
| FW01: pfSense | Routing, VLAN separation, firewall filtering and syslog. | 2 vCPU, 2 GB RAM | Management from VLAN 99 only and deny-by-default rules. |
| APP01: Ubuntu/Nextcloud | Business record portal and database. | 2–4 vCPU, 4–6 GB RAM | HTTPS, TOTP MFA, user groups, SSH keys and patching. |
| MON01: Wazuh | Central dashboard, file integrity, login and vulnerability monitoring. | 4 vCPU, 8 GB RAM | Agent authentication, dashboard roles and retained alerts. |
| BKP01: MinIO/Restic | Encrypted backup repository separated from normal users. | 2 vCPU, 4 GB RAM, 100+ GB | Dedicated credentials, backup VLAN and retention/versioning. |
| WIN11: CLIENT | Office endpoint and test workstation. | 2 vCPU, 4 GB RAM | Standard user, browser MFA and endpoint monitoring. |
| Cloud DR target: stretch | Second encrypted repository outside the local environment. | Small object-storage allocation | Separate account, daily copy and independent recovery test. |

## 7.4 Proposed firewall policy

The firewall policy follows a minimum-access approach. We will allow only the traffic needed for the business and security process. Any other inter-VLAN traffic will be denied and logged.

| Source | Destination | Service | Action | Reason |
| --- | --- | --- | --- | --- |
| Office VLAN | APP01 | TCP 443 | Allow | Users need the business portal. |
| Office VLAN | BKP01, MON01 and management | Any | Block and log | Users must not directly access backup, security or administration systems. |
| APP01 | BKP01 | TCP 9000 | Allow | Restic needs the S3-compatible backup service. |
| APP01 and WIN11 | MON01 | 1514/1515 | Allow | Wazuh agent communication. |
| FW01 | MON01 | 514 | Allow | Central firewall syslog. |
| Management VLAN | Management interfaces | HTTPS/SSH | Allow | Restricted administration. |
| All VLANs | Any other inter-VLAN destination | Any | Deny and log | Default isolation. |

## 7.5 Delivery and evaluation method

Figure 2. Iterative design, build and recovery-evaluation method.

First, we will confirm the business priorities, RTO (Recovery Time Objective), RPO (Recovery Point Objective) and main requirements. Then we will build the network and the first working path between the client and application. After that, identity, monitoring and backup will be added in small parts. Finally, the team will run the safe incident and recovery test, record the measured results and correct any failure before the demonstration.

# 8 Work decomposition and deliverables

The work breakdown structure divides the project into clear packages. Each package has a technical output and an owner. This makes the work easier to plan, review and prove.

| WBS | Work package | Key tasks | Main deliverables |
| --- | --- | --- | --- |
| 1.0 | Initiation and governance | Team charter; GitHub, Projects and Teams; AI log; mentor agreement. | Charter, tool setup, first risk register and approved scope. |
| 2.0 | Business analysis and requirements | Stakeholders; business impact; RTO/RPO; requirements and acceptance criteria. | Requirements catalogue, traceability matrix and success criteria. |
| 3.0 | Architecture and security design | Topology; IP plan; VLANs; firewall rules; identity, hardening and logging design. | Architecture diagram, IP plan and security design. |
| 4.0 | Core environment build | Deploy pfSense, VMs and networks; make baseline snapshots and shared access. | Running virtual environment and configuration exports. |
| 5.0 | Identity and application | Nextcloud, groups, roles, TOTP MFA, TLS and access testing. | Application configuration and access-test evidence. |
| 6.0 | Monitoring and alerting | Deploy Wazuh, enroll agents, receive firewall logs and configure file monitoring. | Monitoring configuration and generated alert evidence. |
| 7.0 | Backup and recovery | MinIO, Restic, scripts, schedule, retention, verification and runbook. | Backup scripts, repository evidence and recovery runbook. |
| 8.0 | Security and recovery testing | Segmentation tests, safe file-change simulation, timed restore, hashes and file counts. | Test plan, logs, screenshots/video and measured results. |
| 9.0 | Quality, risk and change | Peer review, risk updates, change decisions, secret checks and traceability review. | Risk register, quality checklist and approvals. |
| 10.0 | Final communication | Final report, artefact pack, portfolio, live demo and recorded fallback. | Submission package and defended demonstration. |

# 9 Delivery roadmap

The project will use incremental delivery. The team will not wait until the final weeks to connect the components. A basic working environment should appear early and more security controls will be added each week.

| Time | Main work | Evidence or milestone |
| --- | --- | --- |
| Weeks 1–2 | Confirm scenario, team tools, MVP, risks and first lab test. | Repo, Kanban, Teams, checklist and installed platform. |
| Weeks 3–4 | Complete proposal, requirements, acceptance criteria and first design. | Approved proposal, traceability draft and design decisions. |
| Weeks 5–6 | Build pfSense, VLANs, VMs and the first end-to-end client-to-portal path. | Running network skeleton and first connectivity evidence. |
| Weeks 7–8 | Complete Nextcloud roles, MFA, hardening and initial monitoring. | User access tests, hardening checklist and Wazuh events. |
| Week 9 | Complete backup automation, repository isolation and main monitoring rules. | Scheduled snapshot, denied office-to-backup access and alerts. |
| Weeks 10–11 | Run segmentation tests, safe simulation and timed recovery. | RTO/RPO results, hashes, logs and recovery evidence. |
| Week 12 | Fix defects, freeze MVP, complete report and rehearse the demo. | Completed acceptance register and evidence index. |
| Week 13 | Submit final artefacts and complete the live defence. | Final package, live demo and recorded fallback. |

# 10 Team structure, roles and responsibilities

## 10.1 Proposed team roles

| Member | Role | Technical responsibilities | Observable evidence |
| --- | --- | --- | --- |
| Ashraful Abedin Shourab (12298592) | Identity and application lead | Nextcloud, user accounts, role access, TOTP MFA, TLS and user-access tests. | Configuration, screenshots, commits and test evidence. |
| Akib Hossain (12304711) | Network architecture and planning lead | Requirements, architecture, IP plan, pfSense VLANs, firewall design, WBS and roadmap. | Diagrams, tables, exports, commits and network tests. |
| Sheikh Tanvi Mahmud (12297656) | Monitoring and hardening lead | Wazuh deployment, agents, system hardening, alerts, risk and quality evidence. | Wazuh screenshots, logs, checklist, commits and test results. |
| Md Mahafuz Faysal (12281612) | Backup, recovery and integration lead | Restic/MinIO, backup automation, verification, safe simulation and timed restore. | Scripts, snapshots, restore logs, hashes and recovery evidence. |

## 10.2 RACI matrix

| Deliverable / activity | Ashraful Abedin Shourab | Akib Hossain | Sheikh Tanvi Mahmud | Md Mahafuz Faysal | Mentor |
| --- | --- | --- | --- | --- | --- |
| Project proposal and requirements | C | A/R | C | C | I |
| Architecture and IP/firewall design | C | A/R | C | I | C |
| Application, user roles and MFA | A/R | C | C | I | C |
| Wazuh monitoring and hardening | C | C | A/R | I | C |
| Backup and recovery system | I | C | C | A/R | C |
| Safe ransomware-loss simulation | I | C | R | A/R | C |
| Acceptance testing and evidence | R | A/R | R | R | C |
| Risk and quality review | C | R | A/R | C | C |
| Final report and demonstration | R | R | R | A/R | C |

R = Responsible, A = Accountable, C = Consulted and I = Informed.

## 10.3 Task leads for major deliverables

| Major deliverable | Technical lead | Reviewers | Target |
| --- | --- | --- | --- |
| Requirements and traceability | Akib | All members | Week 4 |
| Architecture, IP and firewall design | Akib | Tanvir and Shourab | Week 5 |
| Application, roles and MFA | Shourab | Akib | Week 8 |
| Monitoring and hardening | Tanvir | Akib | Week 9 |
| Backup, recovery and simulation | Faysal | Tanvir and Shourab | Week 11 |
| Final testing and evidence index | All members | Project mentor | Week 12 |
| Final report and demonstration | Faysal / rotating leader | All members and mentor | Week 13 |

# 11. Risk identification and mitigation plan

At first, we identified the technical, security, schedule and teamwork risks of our project. We used likelihood and impact values from 1 to 5. Then we multiplied these values to get the risk score (NIST 2024). The register will not be kept as a one-time document. We will review it in every weekly meeting and update the treatment when the project condition changes.

| ID | RISK | L | I | Rating | Treatment | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| R-01 | Ransomware or stolen credentials can delete the online backup. | 4 | 5 | 20 Extreme | Use a separate backup VLAN, service account, retention and optional offsite copy. | Faysal |
| R-02 | The backup job completes but the data cannot be restored. | 4 | 5 | 20 Extreme | Run weekly checks, sample restore and a full timed recovery. | Faysal |
| R-03 | Recovery misses the RTO because too many steps are manual. | 4 | 4 | 16 Extreme | Use scripts, a clean restore target, a priority sequence and rehearsal. | Faysal |
| R-04 | A lost MFA device locks a user out. | 3 | 3 | 9 High | Use recovery codes, a controlled emergency process and written enrolment steps. | Shourab |
| R-05 | Wazuh misses the mass file change or creates too many alerts. | 3 | 4 | 12 High | Tune file paths and thresholds and generate known test events. | Tanvi |
| R-06 | The lab computer does not have enough RAM, CPU or storage. | 4 | 3 | 12 High | Reduce VM size, start systems in stages, monitor storage and split hosting if needed. | Akib |
| R-07 | The safe simulation changes a file outside the test folder. | 2 | 5 | 10 High | Use an exact allowed path, dry-run mode, synthetic data, snapshot and mentor approval. | Tanvi |
| R-08 | Passwords, keys or real data are uploaded to GitHub. | 3 | 5 | 15 High | Use synthetic data, .gitignore, secret checks and peer review before pushing. | All |
| R-09 | The work is not divided equally or a milestone is missed. | 3 | 4 | 12 High | One owner for every card, weekly evidence and early task redistribution. | Rotating leader |
| R-10 | The cloud cost becomes higher than the approved budget. | 3 | 3 | 9 High | Use a budget cap, alerts and delete unused storage after testing. | Cloud owner |
| R-11 | An internet outage affects the cloud copy or final demo. | 3 | 3 | 9 High | Keep the local MVP independent and prepare a recorded fallback. | Demo lead |
| R-12 | Extra features stop the team from finishing the MVP. | 4 | 4 | 16 Extreme | Freeze the MVP and move new ideas to stretch goals after Week 9. | All |

From the above table we can see that backup deletion, failed restoration, manual recovery and scope growth have the highest initial scores. So these risks will be checked early instead of waiting for final testing.

# 12. Quality management plan (Kerzner 2017)

Our quality approach is based on checking every important output. We will not mark a task as complete only because the document or configuration is created. At first, another member will review it. Then we will connect it with a requirement and test it. Finally, the result and evidence will be stored in the repository.

| Quality area | What we will do | Evidence |
| --- | --- | --- |
| Requirements | Give every Must requirement an ID and connect it to design, implementation and testing. | A reviewed traceability matrix with no missing Must requirement. |
| Technical correctness | Peer review the firewall, scripts, hardening and recovery commands before integration. | A pull request or review record and corrected configuration. |
| Security and privacy | Use synthetic data, remove secrets, apply least privilege and keep the repository private in accordance with recognized information security management practices (ISO/IEC 2022) | Secret scan, repository review and access-test result. |
| Reproducibility | Store configurations, scripts, example environment files and rebuild steps. | A second member can follow the runbook successfully. |
| Testing | Record version, operator, time, expected result, actual result and evidence for each test. | Completed acceptance-test register with Pass or Fail result. |
| Recovery | Measure RPO and RTO and compare file count, hashes and application access. | Timed logs, manifest comparison and user-access check. |
| Documentation | Use the same terms, captions, Harvard references and final proofreading. | A final checklist reviewed by a member other than the writer. |
| Demonstration | Practice the complete scenario and keep a recorded backup. | Demo checklist and fallback recording. |

From the above quality plan, we can see that evidence is required for all main work. This method will reduce the chance of accepting a configuration that looks correct but does not work.

# 13. Tools, technologies and resources

We compared the tools based on cost, available documentation, technical function and suitability for a student lab. Our aim was to select tools that can build a real system without a high license cost.

| Resource | How we use it | Why we selected it |
| --- | --- | --- |
| GitHub private repository | Store configurations, scripts, diagrams, documents, tests and AI-log.md. | It gives time-stamped evidence and supports review. Secrets must not be uploaded. |
| GitHub Projects | Use a Kanban flow from Backlog to Done. | It shows the owner and progress of each task. |
| Microsoft Teams | Keep meetings, decisions, troubleshooting and mentor discussion. | It keeps a searchable record of why a decision was made. |
| VirtualBox, VMware, Proxmox or GNS3 | Run the firewall, servers and client in a virtual environment. | It meets the real-build requirement. The final platform depends on team hardware. |
| pfSense | Create VLAN routing, firewall rules and syslog. | It is widely documented and suitable for a small network lab. |
| Ubuntu LTS and Nextcloud | Run the business record portal and database. | It supports accounts, groups, files, MFA and logs. |
| Wazuh | Collect login, file integrity, firewall and vulnerability events. | It is an open-source monitoring platform suitable for the security part. |
| Restic and MinIO | Create encrypted backups and store them in an isolated S3-compatible repository. | They support scripting, snapshots, checking and recovery testing. |
| Python, Bash and PowerShell | Automate backup, test data, verification and network tests. | Automation makes the work repeatable and meets the capstone requirement. |
| Optional cloud storage | Keep a second encrypted backup outside the local lab. | This is a stretch goal and the cost must be approved first. |

From the above tools we found that the main MVP can be completed using open-source or community software. The team only needs to choose one virtualization platform. Using many platforms together can make the project difficult to rebuild.

## 13.1 Indicative resource and budget plan

| Item | Quantity / allowance | Estimated cost | Control |
| --- | --- | --- | --- |
| Existing student computers or shared virtual host | Team provided | AU$0 direct purchase | Check capacity in Week 2 and start VMs in stages if required. |
| Community and open-source software | All main MVP tools | AU$0 license cost | Check license conditions and edition limits. |
| Optional cloud object storage | Small test allocation | Maximum AU$50 for the team | Use budget alerts and delete the storage after the project. |
| External drive or extra storage | Only when required | [Need an approved amount] | Get approval first and store synthetic data only. |
| Contingency | 10% of the approved cash budget | [Amount will be provided later] | Use only after team agreement. |

# 14. Feasibility analysis

A technical feasibility analysis is carefully carried out in order to determine a professional investment strategy (Gürtürk, Erdem & Uçar 2024). After selecting the tools and project scope, we analyzed whether the project can be completed in this term. We checked the technical, schedule, operational, economic, safety and teamwork feasibility.

| Feasibility area | Assessment |
| --- | --- |
| Technical feasibility | The tools can run on student virtualization hardware and have clear setup documents. We will test resource use and integration early. |
| Schedule feasibility | The roadmap builds a network skeleton and one thin working process by the middle of the term. Stretch goals will wait until the MVP is stable. |
| Operational feasibility | The user will use a web portal, TOTP and short runbooks. This is suitable for a small office without dedicated IT staff. |
| Economic feasibility | The MVP mainly uses existing hardware and free or community software. Cloud use is optional and capped. |
| Safety and ethical feasibility | Only synthetic data and a limited test directory will be used. Real ransomware and uncontrolled destructive testing are excluded. |
| Team feasibility | Every member has one technical workstream. Weekly commits, Kanban updates and mentor demonstrations will show problems early. |

From the above analysis we can see that the project is feasible if the team completes the main build early and controls the scope. The biggest limitation is hardware capacity and integration time, so these will be tested before the final weeks.

# 15. Professional, ethical and security considerations

The team must work responsibly and safely because this project involves security and data recovery. We will use the following rules during the project (NIST 2018):

Use synthetic data only and do not collect unnecessary personal or business information.

Keep the repository private and remove passwords, tokens, public IP addresses and identifying screenshots before submission.

Do not run real ransomware or test a system without clear ownership and permission.

Use dry-run mode by default and restrict the simulation to the approved test folder.

Tell users what monitoring is used and collect only the events needed for security and recovery.

Check software licenses and give credit for third-party code, documents and diagrams.

Record important AI use in AI-log.md, check the output and understand every submitted artefact.

Refer legal, privacy, insurance and notification questions to qualified advisers instead of giving legal advice.

So, from these considerations we decided that safety and privacy will be included in the technical design, not only written at the end. The simulation, screenshots and repository will be checked before they are shared.

# 16. Communication, Governance and Progress Evidence

This section describes how Group PG5 organizes, documents, and maintains evidence of their teamwork throughout the term, and how that evidence is expected to reflect each member's individual contributions rather than just the group's collective output. The team implements the unit's teamwork framework without any alternatives: a personal GitHub repository, a Microsoft Teams workspace, and a GitHub Projects (Kanban) board. Together, these three tools create a seamless, time-stamped record of who did what, when, and why. The assessment of individual contributions in this unit is based on this observable evidence rather than on end-of-term claims, so the governance model below is treated as a distinct project deliverable rather than an administrative burden.

Since AG-3 is completed by four members, each responsible for a distinct technical workstream (Identity & MFA, Network & Firewalling, Monitoring & Hardening, and Backup/Recovery), the communication and governance model must make sense of the four parallel streams of work as a cohesive project. The following framework repository layout, Kanban convention, Teams channel, meeting continuity, AI transparency, and evidence indexing is specifically designed to maintain that readability from week one to the final showcase.

## 16.1 GitHub Repository Structure and Commit Discipline

| Path | Contents |
| --- | --- |
| /README.md | Project overview, environment build/run instructions, team roles |
| /docs | Design docs, IP/VLAN plan, security policy, hardening baseline, runbooks, test plans |
| /configs | pfSense, Nextcloud, Wazuh, Restic/MinIO configuration exports (secrets removed) |
| /topologies | Network and architecture diagrams, and virtualization project files (such as GNS3/VirtualBox project exports) |
| /script | Automation code: backup, verification, simulation and environment-rebuild scripts (Bash/Python/PowerShell) |
| /testing | Acceptance-test plans, test results, screenshots, logs, and RTO/RPO measurement records |
| /evidence | Per-member evidence folders (see Section 16.7), each containing that member's dated, attributable proof of work |
| /AI-log.md | A single, running, dated record of all meaningful AI-assisted work across the team |

Commit discipline is treated with equal importance, just like code or configuration. Each commit uses a conventional prefix (feat/fix/docs/test) and a specific, reviewable message instead of a vague summary. Representative commits from Faisal's own workstream include:

| Member | Example Commits |
| --- | --- |
| Faysal | feat: configure encrypted Restic repository feat: add 4/5/6-hour backup schedule test: perform timed clean-snapshot recovery |
| Shourab | feat: configure Nextcloud users and role groups feat: enable mandatory TOTP MFA test: verify restricted folder access |
| Akib | feat: configure pfSense VLAN interfaces feat: apply deny-by-default firewall rules test: record inter-VLAN connectivity |
| Tanvi | feat: connect app server to Wazuh feat: configure file-integrity monitoring test: generate and document Wazuh alerts |

A commit history made up of such small, frequent, and well-described commits spread out over the entire term rather than concentrated around deadlines is itself part of the evidence that the unit values ​​under "continuous, decentralized work."

## 16.2 Kanban Card-Naming Rules

The board uses the standard column flow:

Backlog → To Do → In Progress → Review → Testing → Deployed → Done.

To keep the board readable across 4 members, every card follows the pattern:

[Owner-initial] Short task description e.g. [F] Configure Restic encrypted repository.

Every card has exactly one owner and one label (e.g. backup, automation, testing, ai-assisted).

A card is linked to the commit or pull request that completed it before it moves to Done.

A card left in In Progress for more than a week is raised at the next Tuesday meeting.

Representative Cards (Example):

| Owner | Example Card | Week |
| --- | --- | --- |
| F | Configure Restic encrypted repository (backup) | 5 |
| F | Live timed recovery + RTO/RPO calculation (testing) | 11-12 |
| S | Enable and test TOTP-based MFA (identity) | 7 |
| A | Apply deny-by-default firewall rules (security) | 6-7 |
| T | Configure file-integrity monitoring (security) | 7 |

## 16.3 Microsoft Teams Channel Structure and Meeting Cadence

#general · #technical-discussion · #problem-solving · #documentation · #aI-usage Decisions and problem-solving are documented here, so they remain searchable evidence and don’t get lost in a call or DM.

Weekly meeting: Tuesday 4:30–4:45 PM. Each member reports what they did, what they’ll do next, and if there are any obstacles; the team checks the risk register, the progress of the MVP, and whether anything is happening. Meeting minutes (attendance, to-dos, decisions, obstacles) are logged into Teams the same day using a permanent template stored in the /docs/meeting-minutes/ folder.

## 16.4 AI Transparency and the AI-log

Per the Teamwork Framework, architectural and design decisions remain the team's responsibility even when AI drafts or assists; every AI-assisted artefact must be explainable by the member who used it. Each member maintains a dated evidence folder in /evidence/<name>/, so that contributions are individually verifiable:

| Member | Core Evidence Maintained |
| --- | --- |
| Faysal | Restic/MinIO config, backup logs, simulation script, recovery timestamps, RTO/RPO calculation, SHA-256 comparison |
| Shourab | Nextcloud user/role config, MFA enrolment + pass/fail login evidence, access-denial proof |
| Akib | pfSense/VLAN config, firewall rule screenshots, allowed vs blocked connectivity results |
| Tanvi | Wazuh dashboard/alerts, before-after hardening checklist, risk-register versions |

## 16.5 Weekly Proof Checklist

Reviewed at Tuesday's meeting; applies equally to four lines of action:

| Source | Minimum Weekly Proof |
| --- | --- |
| GitHub | At least one meaningful, reviewable commit |
| Kanaban | Owned cards moved and linked to completed work |
| Teams | Visible record of decisions and troubleshooting |
| AI-log | Entry showing tools, purpose, change and validation |

# 17. Group Contribution Declaration

All four members of Group PG5 confirm that they have each contributed equally to drafting the sections assigned to the proposal and to handling the technical aspects of their respective workstreams. Each member assumes full responsibility for the content, quality, and accuracy of their own contributions.

| Student | Contribution to this Documents | Percentage | Confirmation |
| --- | --- | --- | --- |
| Shourab | Executive summary + Sections 1-5; Nextcloud identity/MFA | 25% | YES |
| Akib | Sections 6-10; network/pfSense/VLAN/firewall | 25% | YES |
| Tanvi | Sections 11-15; Wazuh monitoring and OS hardening | 25% | YES |
| Faysal | Sections 16-18 + Conclusion; Restic/MinIO backup and recovery | 25% | YES |

Total Contribution: 100%

# 18. Conclusion

This proposal outlines a realistic, appropriately complex, and security-focused final project for Plains Pastoral Co. It addresses the genuine business risks of ransomware and prolonged outages through a multi-component environment-designed, built, and demonstrated that integrates identity and access control, network segmentation, security hardening, centralized monitoring, automated encrypted backups, and a tested, time-bound recovery system.

Four technical workstreams Identity & MFA (Shourab), Network Architecture & Firewalls (Akib), Monitoring & Hardening (Tanvi), and Backup, Automation & Recovery (Faysal) converge into a single end-to-end demonstration: a user authenticates via MFA and accesses only authorized services across a segmented network; Wazuh monitors and records security events; a controlled, simulated ransomware incident is contained; and the team completes recovery from an isolated, verified backup within agreed Recovery Time and Recovery Point objectives.

The key measure of success is not merely the existence of individual controls, but demonstrated and measurable evidence: detection of a controlled simulated breach, selection of an error-free recovery point, restoration of prioritized records and applications, integrity verification via file counts and hash comparisons, and reporting of RTO/RPO metrics against agreed targets. Consistent with the standards applied to every NIS capstone project, the initiative will also demonstrate professional teamwork through sustained and distributed technical contributions, requirements traceability, an active risk register, transparent AI usage, and defensible, evidence-based documentation.

# References

- International Organization for Standardization (ISO) 2019, ISO 22301:2019 Security and resilience — Business continuity management systems.

- National Institute of Standards and Technology (NIST) 2024, The NIST Cybersecurity Framework 2.0.

- International Organization for Standardization 2018, ISO/IEC/IEEE 29148:2018 Systems and software engineering — Life cycle processes — Requirements engineering.

- International Organization for Standardization (ISO) & International Electrotechnical Commission (IEC) 2022, ISO/IEC 27001:2022 Information security, cybersecurity and privacy protection—Information security management systems—Requirements, ISO, Geneva.

- Australian Cyber Security Centre (ACSC) 2024, Essential Eight Maturity Model, Australian Signals Directorate, Canberra.

- National Institute of Standards and Technology 2020, SP 800-207 Zero Trust Architecture.

- Gürtürk, M, Erdem, M & Uçar, F 2024, ‘Solar energy technical feasibility comparison: an alternative proposal for the industry’, Energy Efficiency, vol. 17, article 41. DOI: 10.1007/s12053-024-10226-9

- Kerzner, H 2017, Project management: a systems approach to planning, scheduling, and controlling, 12th edn, E-book, John Wiley & Sons, Hoboken, New Jersey.

- NIST 2018, Risk Management Framework for Information Systems and Organizations: A System Life Cycle Approach for Security and Privacy (SP 800-37 Rev. 2), National Institute of Standards and Technology, viewed 25 July 2026, https://doi.org/10.6028/NIST.SP.800-37r2

- National Institute of Standards and Technology 2022, SP 800-215 Guide to a Secure Enterprise Network Landscape.

- National Institute of Standards and Technology 2009, SP 800-41 Rev. 1 Guidelines on Firewalls and Firewall Policy.

- Netgate 2026, pfSense VLAN and firewall documentation.

- Cybersecurity and Infrastructure Security Agency 2023, StopRansomware Guide.

- CQUniversity Australia 2026, NIS Capstone — Capstone Checklist and Teamwork Framework.

- National Institute of Standards and Technology 2024, Cybersecurity Framework 2.0 and Small Business Quick-Start Guide.

# Appendix C — Final Integration Checklist

To be completed jointly before submission and the final demonstration:

Each member must have visible technical work, not just written components.

Each 'Must' requirement must be linked to a design item, an implementation item, and a test result.

Evidence from GitHub, Kanban, and Teams must span the entire term; it cannot simply be uploaded at the end.

Screenshots and logs must include dates, usernames, or other proof of ownership where possible.

Live recovery times must be measured, and actual test measurements—rather than estimates—must be used for RTO/RPO calculations.

AI logs must explain what the AI ​​generated, what changes the team made, and how the result was verified.

The final report must not claim any tests or features that cannot be demonstrated live.

The 'Table of Contents' field in Word must be updated before submission.

All four members must agree on the percentages in Section 17, and the total sum must equal 100%.

References and Appendices A–C have been verified for consistency with the final document.